## 🏠 Dashboard
🛍️ TIANGGE — PRODUCT MOTHERBOARD
Local bazaar discovery platform for the Philippines · Gen Z focused, mobile-first
📊 QUICK STATS
📋 Total Leads | 🔥 Hot Leads | 💰 Total Revenue | 💸 Total Costs | 📣 Campaigns | 📌 Backlogs | ✅ Tasks Done | 📈 Net Margin
leads | qualified | PHP | PHP | active | items | done | PHP
📌 QUICK NAVIGATION
📋 Leads Tracker |  | 📌 Product Backlog |  | 📣 Marketing Tracker |  | 💰 Sales Pipeline
Track & manage your leads pipeline |  | Features, bugs, sprints |  | Campaigns, content, KPIs |  | Deals, revenue, forecasts
💸 COSTS VS REVENUE
Category | Budget (PHP) | Actual (PHP) | Remaining | % Used
Marketing
Tech / Dev
Ops / Admin
Sales
TOTAL

## 📋 Leads
📋 LEADS TRACKER — TIANGGE
Track all potential merchants, partners, and users here. Update status after every touchpoint.
ID | Name | Business / Brand | Contact | Status | Source | Lead Type | Date Added | Last Contact | Next Action | Expected Value (PHP) | Notes
L-001 | Maria Santos | Cute Crafts PH | 0917-123-4567 | New | Instagram | Merchant | 2025-01-15 | 2025-01-15 | Send intro deck | 5000 | Handmade accessories seller
L-002 | Juan Dela Cruz | Lutong Bahay ni Juan | 0918-234-5678 | Contacted | Referral | Merchant | 2025-01-16 | 2025-01-18 | Follow-up call | 8000 | Home cook, wants to sell ulam
L-003 | Belle Reyes | BelleK Beauty | 0919-345-6789 | Qualified | TikTok | Merchant | 2025-01-17 | 2025-01-20 | Onboarding call | 12000 | Skincare reseller, 10k followers
L-004 | Pinoy Thrift Co. | Pinoy Thrift Co. | hello@pinoythrift.com | Converted | Word of Mouth | Merchant | 2025-01-10 | 2025-01-22 | — | 15000 | Already onboarded ✅
L-005 | SM North EDSA | SM Supermalls | partnerships@sm.com | Lost | Cold Outreach | Partner | 2025-01-05 | 2025-01-15 | — | 50000 | Not interested at this time

## 📌 Backlog
📌 PRODUCT BACKLOG — TIANGGE
Track all features, bugs, improvements, and sprint items. Update priority + status regularly.
ID | Title | Type | Priority | Status | Sprint | Assignee | Estimate (hrs) | Actual (hrs) | Due Date | Notes
B-001 | Merchant Registration Flow | Feature | 🔴 Critical | Done | Sprint 1 | Dev Team | 16 | 18 | 2025-01-20 | Core onboarding flow complete
B-002 | Product Listing Page | Feature | 🔴 Critical | Done | Sprint 1 | Dev Team | 24 | 24 | 2025-01-20 | Completed and QA'd
B-003 | Search & Filter UX | Feature | 🟠 High | In Progress | Sprint 2 | Dev Team | 20 | 10 | 2025-02-05 | Filter by category + barangay
B-004 | Fix image upload bug | Bug | 🔴 Critical | In Progress | Sprint 2 | Dev Team | 4 | 2 | 2025-01-30 | Mobile images failing on upload
B-005 | Merchant Dashboard Analytics | Feature | 🟡 Medium | Planned | Sprint 3 | Dev Team | 30 | 0 | 2025-02-20 | Views, clicks, inquiries per listing
B-006 | Push Notifications | Feature | 🟡 Medium | Planned | Sprint 3 | Dev Team | 16 | 0 | 2025-02-20 | New listings near user
B-007 | Gen Z UI Polish | Design | 🟠 High | Planned | Sprint 2 | Design Team | 12 | 0 | 2025-02-10 | Vibe check with target users
B-008 | Payment Integration (GCash) | Feature | 🟠 High | Planned | Sprint 4 | Dev Team | 40 | 0 | 2025-03-01 | In-app payment for featured slots
B-009 | User Reviews System | Feature | 🟢 Low | Planned | Sprint 4 | Dev Team | 20 | 0 | 2025-03-15 | Star ratings + comments
B-010 | Performance Audit | Research | 🟡 Medium | Planned | Sprint 3 | Dev Team | 8 | 0 | 2025-02-20 | Core Web Vitals check

## 📣 Marketing
📣 MARKETING TRACKER — TIANGGE
Track campaigns, content, budgets, and KPIs. Gen Z platforms: TikTok, IG Reels, Facebook Groups.
ID | Campaign / Content | Type | Platform | Status | Target Audience | Start Date | End Date | Budget (PHP) | Spent (PHP) | Reach | Engagements | Notes
M-001 | Tiangge Launch Tease | Organic Content | TikTok | Done | Gen Z 18-25 NCR | 2025-01-10 | 2025-01-14 | 0 | 0 | 45000 | 8200 | Viral hook video ft. local sellers
M-002 | Merchant Sign-Up Drive | Paid Ad | Facebook | Active | SMB Owners PH | 2025-01-15 | 2025-02-15 | 5000 | 3200 | 22000 | 1100 | CPM ₱45, CTR 3.2%
M-003 | Behind the Tiangge Series | Organic Content | Instagram | Active | Gen Z 18-28 PH | 2025-01-20 | 2025-02-20 | 0 | 0 | 12000 | 2300 | Weekly merchant feature reel
M-004 | Valentine's Bazaar Promo | Paid Ad | TikTok | Planned | 18-30 PH All Gender | 2025-02-01 | 2025-02-14 | 8000 | 0 | 0 | 0 | Spark Ads — Feb 14 angle
M-005 | Referral Program Launch | Email / SMS | Email | Planned | Existing Users | 2025-02-10 | 2025-02-28 | 2000 | 0 | 0 | 0 | Refer a seller, get discount
M-006 | Summer Tiangge Fest | Event | Facebook | Planned | All Metro Areas | 2025-03-15 | 2025-03-16 | 15000 | 0 | 0 | 0 | IRL bazaar event + digital launch

## 💰 Sales
💰 SALES PIPELINE — TIANGGE
Track all revenue opportunities — merchant subscriptions, featured listings, partnerships, and sponsorships.
ID | Deal / Account | Deal Type | Stage | Owner | Date Created | Expected Close | Deal Value (PHP) | Monthly Recurring (PHP) | Probability % | Actual Revenue (PHP) | Notes
S-001 | BelleK Beauty - Featured Listing | Featured Slot | Closed Won | Jhai | 2025-01-17 | 2025-01-22 | 2500 | 2500 | 100% | 2500 | Monthly recurring, renews Feb
S-002 | Pinoy Thrift - Merchant Sub | Subscription | Closed Won | Jhai | 2025-01-10 | 2025-01-15 | 500 | 500 | 100% | 500 | Basic plan, ₱500/mo
S-003 | Lutong Bahay - Featured Listing | Featured Slot | Negotiation | Jhai | 2025-01-18 | 2025-02-01 | 2500 | 2500 | 70% | 0 | Negotiating on package price
S-004 | SM Supermalls Partnership | Partnership | Prospect | Team | 2025-01-05 | 2025-03-01 | 50000 | 0 | 20% | 0 | Long shot but worth pursuing
S-005 | Valentine's Event Sponsor - TBD | Sponsorship | Proposal Sent | Team | 2025-01-20 | 2025-02-01 | 10000 | 0 | 60% | 0 | Sent deck to 3 local brands
S-006 | Maria Santos - Merchant Sub | Subscription | Prospect | Jhai | 2025-01-15 | 2025-02-05 | 500 | 500 | 40% | 0 | Still reviewing the platform
TOTAL

## 💸 Costs
💸 COSTS & BUDGET TRACKER — TIANGGE
Track all expenses by category. Budget columns drive the Dashboard summary cards.
ID | Description | Category | Amount (PHP) | Budget (PHP) | Payment Date | Payment Method | Vendor / Payee | Receipt # | Notes
C-001 | TikTok Ads — January | Marketing | 3200 | 5000 | 2025-01-31 | GCash | TikTok Ads | TT-001 | Merchant Awareness campaign
C-002 | Facebook Boost — Launch | Marketing | 1800 | 3000 | 2025-01-20 | GCash | Meta Ads | META-001 | Launch week boost
C-003 | AWS Hosting (3 months) | Tech / Dev | 4500 | 6000 | 2025-01-15 | Credit Card | Amazon Web Services | AWS-INV-001 | EC2 + RDS setup
C-004 | Domain + SSL | Tech / Dev | 800 | 1000 | 2025-01-01 | Credit Card | Namecheap | NC-2025-001 | tiangge.ph domain
C-005 | Figma Professional | Design | 1200 | 1200 | 2025-01-01 | Credit Card | Figma Inc. | FIG-001 | Annual plan prorated
C-006 | Freelance Content Creator | Marketing | 5000 | 5000 | 2025-01-15 | Bank Transfer | Marco Reyes | FREELANCE-001 | 3 TikTok videos
C-007 | Printing — Flyers & Tarpaulins | Ops / Admin | 2500 | 3000 | 2025-01-18 | Cash | Print Express | PRE-001 | For bazaar events
C-008 | Google Workspace | Ops / Admin | 1100 | 1100 | 2025-01-01 | Credit Card | Google | GWS-001 | Team email + Drive
C-009 | Sales Commission — January | Sales | 600 | 800 | 2025-01-31 | Bank Transfer | Team | COMM-001 | 2% of closed revenue
C-010 | Valentine's Event Venue Deposit | Ops / Admin | 5000 | 10000 | 2025-01-25 | Bank Transfer | Venue XYZ | VEN-001 | 50% deposit paid
TOTAL